## Action Tracker
sno | points | additional info | responsible person | status | exact status
1 | Amazon Quick vs M365 Copilot Comparison (Cost) | Compared cost details for both platforms. | Nishant (Amazon Quick) & Wilson (M365 Copilot) | completed | Cost details obtained from Nishant and Wilson.
2 | Custom Chat Agents | Built custom chat agents with the given Sales Knowledge for both Quick & M365 Copilot. | Team / Developer | completed | Chat agents built successfully with sales knowledge.
3 | Power Automate Workflow | Implemented power Automate workflow for file approvals (triggers when a new file is added). | Team / Developer | completed | Workflow successfully implemented for file approvals upon new file addition.
4 | AWS Quick Team Follow-up (Source References) | Source references open in a new page instead of comparative sideways view (unlike M365 Copilot). | AWS Quick Team | completed | Followed up. AWS Quick team noted they cannot change this, but offer it as a feature.
5 | AWS Quick Team Follow-up (Predefined Prompts) | Predefined prompts execute immediately upon click; cannot edit/upload files directly (requires copy-pasting custom prompts). | AWS Quick Team | completed | Followed up. AWS Quick team noted this is how the feature works.
6 | SharePoint Access | Got Access to the SharePoint site. | Wilson (IT) | completed | Wilson (IT) has created a separate SharePoint for our usecase.
7 | Design Files Received | Manoj Kalathil shared the design files via mail. Need to use them for our chat agents. | Manoj Kalathil | completed | Design files received via mail.
8 | Presentation Agent with Design Files | Create presentation agent using design files given by Manoj Kalathil (for both Amazon Quick and M365 Copilot). | Team / Developer | yet to start | Pending implementation using received design files.
9 | OneDrive Update & Deletion Workflow | Automate update and deletion flows linking OneDrive and SharePoint via Power Automate. | Team / Developer | yet to start | Pending configuration.
10 | SharePoint Sales Knowledge Update | Update sales knowledge files stored on SharePoint. | Team / Developer | in progress | Knowledge files identified; update in progress.
11 | Notification System for Inactive Files | Set up Power Automate notification if a file remains unmodified for more than 15 days. | Team / Developer | yet to start | Pending workflow setup.
12 | Excel Tracker Creation | Create an Excel tracker to monitor all action points, status, and responsibilities. | Mohammed Thalha M | completed | Excel tracker created successfully.
13 | Follow-up: Microsoft Limitation | Discuss Microsoft limitation points. | Wilson (IT) | yet to start | Follow-up pending with Wilson (IT).
14 | Follow-up: Copilot Studio Credits | Check and verify Copilot Studio credits. | Wilson (IT) | yet to start | Follow-up pending with Wilson (IT).
15 | Follow-up: Quick Connectors (OneDrive & SharePoint) | Review connectors setup for Amazon Quick with OneDrive & SharePoint. | Nishant (DevOps) | yet to start | Follow-up pending with Nishant (DevOps).
16 | Follow-up: Salesforce Integration Scope | Determine exact requirements and tasks for Salesforce integration. | Wilson / Shraddha | yet to start | Clarification pending on what needs to be done.
17 | Follow-up: Employee Skillset Source | Identify source and contact person to get the skillset of employees. | Management / HR | yet to start | Pending clarification on who will provide employee skillset data.